## Checklist
Step # | Phase | Key Questions | Owner | Due Date | Status | Evidence/Links | Notes | Gate Criteria Met? | Gate Decision
1 | Define Objectives | What outcomes are we trying to achieve? What problems are we solving?
2 | Build a Cross-Functional Team | Identify sponsor, clinical, data, IT, legal/privacy, finance, and training leads.
3 | Feasibility & Risk Assessment | Assess data availability/quality, workflow impact, risks, and constraints.
4 | Vet Industry Partners & Technologies | Evaluate vendors, model choices, integration paths, and security posture.
5 | Establish Ethical Guardrails | Align with Ethical AI Pledge; define use policy, human oversight, and transparency.
6 | Develop Implementation Plan | Timeline, budget, roles, comms, training, integration, rollout and rollback plans.
7 | Train & Engage Staff | Prepare end users; create materials, sandbox, and feedback loops.
8 | Monitor & Evaluate Performance | Define success metrics; set baseline/targets; plan audits and bias checks.
9 | Oversight & Governance | Stand up governance cadence; document decisions and approvals.
10 | Scale Responsibly | Expand in phases with controls; revalidate risk & ethics at each stage.
11 | Repeat the Cycle | Continuous improvement—feed findings back into objectives.

## Stage Gates
Step # | Phase | Acceptance Criteria (examples)
1 | Define Objectives | Problem statement approved; success metrics drafted; scope documented.
2 | Build a Cross-Functional Team | RACI assigned; sponsor confirmed; meeting cadence scheduled.
3 | Feasibility & Risk Assessment | Data/proc feasibility documented; risk register created; mitigations planned.
4 | Vet Industry Partners & Technologies | Shortlist completed; security/BAA reviewed; integration path agreed.
5 | Establish Ethical Guardrails | Ethical use policy published; bias test plan set; human-in-loop defined.
6 | Develop Implementation Plan | Timeline/budget signed; rollback plan; comms + training plan finalized.
7 | Train & Engage Staff | Training delivered; ≥80% staff assessed competent; feedback resolved.
8 | Monitor & Evaluate Performance | Baseline captured; KPI dashboard live; audit schedule defined.
9 | Oversight & Governance | Governance charter approved; decisions and logs repository live.
10 | Scale Responsibly | Pilot success met; risks re-evaluated; change mgmt plan updated.
11 | Repeat the Cycle | Retrospective completed; next objective drafted; updates shared.

## Risk Register
Risk ID | Step | Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Priority | Mitigation | Owner | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## RACI
Task | Exec Sponsor | Clinical Lead | IT Lead | Data/Analytics | Privacy & Legal | Finance | Training Lead | Ops Leader | Vendor PM | Valid? (1 A)
Define Objectives
Build a Cross-Functional Team
Feasibility & Risk Assessment
Vet Industry Partners & Technologies
Establish Ethical Guardrails
Develop Implementation Plan
Train & Engage Staff
Monitor & Evaluate Performance
Oversight & Governance
Scale Responsibly
Repeat the Cycle

## KPIs
Metric | Definition | Baseline | Target | Collection Method | Frequency | Owner | Notes
Time to decision | Avg time from request to approval/deny |  |  | EHR + workflow logs | Monthly
Clinical outcome (e.g., sepsis alerts PPV) | Positive predictive value of AI-triggered alerts |  |  | Clinical audit | Quarterly
Staff time saved | Hours saved per week via automation |  |  | Time-motion study | Monthly
Cost avoidance / ROI | Estimated annual savings or revenue impact |  |  | Finance model | Quarterly

## Ethics & Guardrails
Item | Status | Evidence/Links | Owner | Notes
Documented purpose & boundaries of use
Human-in-the-loop decision checkpoints
Bias testing plan and results recorded
Data minimization & PHI handling defined
Transparency statement for end users
Model/version & change log captured
Audit logs enabled & reviewed
Incident response & rollback plan
Third-party/vendor obligations (BAA/SCC)
Explainability guidance for clinicians

## Vendor Vetting
Vendor | Tool | Use Case | Hosting/Region | Security (BAA, SOC 2) | API/Interoperability | EHR Integration Path | Pricing Model | Notes | Fit Score (1-5)

## Dashboard
Metric | Value | Notes
Steps Complete % |  | Share of steps marked Complete
Gates GO |  | Steps ready to advance
Open High Risks |  | High = Risk Score ≥ 15 and not complete
Ethics Items Complete |  | Out of 10